## Project Roadmap
mediaERP -- PROJECT MANAGEMENT HUB
DELTA MEDIA ANALYTICS & REPORTS ¦ 8 Phases - 67 Features ¦ FastAPI - MongoDB - Next.js 15 - Claude AI
Wk | Phase | Deliverables | Start Date | End Date | Done | Priority | Owner | 1 | Blockers / Notes | Approved By
1 | Scaffold + Auth | Mono-repo, FastAPI+Motor+CORS+health, JWT auth (register/login/refresh/me/logout), bcrypt, Next.js 15, Tailwind, shadcn/ui, DM Sans, axios.ts, animations.ts, Zustand, Login+Register pages, Route guard | 2026-05-11 | 2026-05-17 | Not Started | Critical | Full Stack Dev | 0%
2 | Connector System | Connector CRUD + AES-256 token encryption, Google Ads OAuth2, GA4 OAuth2, Facebook Ads OAuth2, ConnectorGrid, ConnectorCard, AddConnectorModal, SyncStatusBadge, OAuthCallback | 2026-05-18 | 2026-05-24 | Not Started | Critical | Full Stack Dev | 0%
3 | Sync Pipeline | Marketing data model + compound index, Celery+Redis+Beat, sync_connector task (retry x3), Google/GA4/Facebook fetch_data, LinkedIn OAuth+sync, TikTok OAuth+sync (5 platforms total), frontend live status | 2026-05-25 | 2026-05-31 | Not Started | High | Backend Dev | 0%
3-4 | Reports API + Charts | GET /reports/overview (agg+delta), /campaigns (paginated), /trend (time-series), POST /custom, saved reports CRUD, CSV export, DataTable, Pagination, DateRangePicker, KpiCard, SpendTrendChart, PlatformDonut, CampaignBarChart, RoasGauge | 2026-05-25 | 2026-06-07 | Not Started | High | Full Stack Dev | 0%
4-5 | Dashboard UI Polish | Sidebar+Header+uiStore, Overview page (KPIs+charts+campaigns), Campaigns page (DataTable+filters), MetricSelector+FilterPanel+ReportBuilder, Reports list+detail+CSV export | 2026-06-01 | 2026-06-14 | Not Started | High | Frontend Dev | 0%
5-6 | Claude AI Layer | ai_service.py NL->pipeline->execute->explain, POST /ai/query + GET /ai/history, useAi.ts, AiQueryPanel + AiResultCard (Framer Motion reveal), ai/page.tsx | 2026-06-08 | 2026-06-21 | Not Started | Medium | AI Dev | 0%
6 | Settings + Notifications | PUT /auth/me + /password, notifications model + emit on sync events, Settings page (profile/password/plan/API key tabs), NotificationBell (badge+dropdown+polling+Sonner) | 2026-06-15 | 2026-06-21 | Not Started | Medium | Full Stack Dev | 0%
7 | Deployment | Docker Compose (6 services+healthchecks), backend Dockerfile (multi-stage), frontend Dockerfile (standalone), Railway (FastAPI+Celery), Vercel (Next.js), MongoDB Atlas M0, Upstash Redis, Sentry, docs | 2026-06-22 | 2026-06-28 | Not Started | Medium | DevOps | 0%
8 | QA + Polish | 4-case test coverage all features, Framer Motion audit, dark mode audit, mobile audit (375px/1280px), error handling edge cases, performance testing, PROJECT_STATUS.md final update | 2026-06-29 | 2026-07-05 | Not Started | Low | QA Lead | 0%
PHASE SUMMARY
Total Phases | Completed | In Progress | Not Started | Overall Progress
9

## Task Tracker
TASK TRACKER -- Feature-Level Breakdown ¦ 67 Features Across 8 Phases
# | Phase | Feature | Description | Assigned To | Start | Due | Status | Layer | Est Hrs | Actual Hrs | Notes / PR Link
1.1 | Ph1 | Mono-repo Skeleton | backend/ and frontend/ dirs, .gitignore, docker-compose.yml skeleton, README.md, PROJECT_STATUS.md | DevOps | 2026-05-11 | 2026-05-11 | Done | Infra | 3
1.2 | Ph1 | Backend Bootstrap | main.py, config.py, database.py, utils/response.py (success/error helpers), /health endpoint, CORS | Backend Dev | 2026-05-11 | 2026-05-11 | Done | Backend | 4
1.3 | Ph1 | Backend History Stubs | Create empty mistakes.md, servicesHistory.md, middlewareHistory.md, features.md in backend/ | Backend Dev | 2026-05-11 | 2026-05-11 | Done | Backend | 1
1.4 | Ph1 | Frontend Bootstrap | Pinned packages, DM Sans via next/font, app/layout.tsx, lib/axios.ts (bearer+401 logout), lib/animations.ts all variants | Frontend Dev | 2026-05-12 | 2026-05-12 | Done | Frontend | 5
1.5 | Ph1 | Frontend Providers | QueryProvider.tsx (RQ+Devtools), ThemeProvider.tsx (next-themes defaultTheme=system), Sonner Toaster in layout | Frontend Dev | 2026-05-12 | 2026-05-12 | Done | Frontend | 2
1.6 | Ph1 | Frontend History Stubs | Create empty mistakes.md, componentsHistory.md, apiHistory.md, features.md, design.md in frontend/ | Frontend Dev | 2026-05-12 | 2026-05-12 | Done | Frontend | 1
1.7 | Ph1 | Auth Models & Utils | models/user.py, utils/jwt.py (create_access/refresh/decode tokens), utils/encryption.py (AES-256-GCM), unique email index | Backend Dev | 2026-05-13 | 2026-05-13 | Done | Backend | 4
1.8 | Ph1 | Auth Middleware | middleware/auth.py get_current_user (JWT validate+inject user), middleware/permissions.py require_plan() dep | Backend Dev | 2026-05-13 | 2026-05-13 | Done | Backend | 3
1.9 | Ph1 | Auth -- Register & Login | services/auth_service.py (register_user, authenticate_user, bcrypt), POST /auth/register, POST /auth/login, schemas/auth.py | Backend Dev | 2026-05-13 | 2026-05-14 | Done | Backend | 6
1.10 | Ph1 | Auth -- Refresh / Me / Logout | POST /auth/refresh (rotate access token), GET /auth/me (current user), POST /auth/logout (revoke refresh token) | Backend Dev | 2026-05-14 | 2026-05-14 | Done | Backend | 4
1.11 | Ph1 | Auth Store + Hook | lib/stores/authStore.ts (Zustand: user/token/setSession/logout), hooks/useAuth.ts mutations, types/user.ts IUser shape | Frontend Dev | 2026-05-15 | 2026-05-15 | Done | Frontend | 5
1.12 | Ph1 | Shared UI -- First Batch | ThemeToggle (AnimatePresence sun/moon swap), PageHeader, LoadingSkeleton, EmptyState -- log each in componentsHistory.md | Frontend Dev | 2026-05-15 | 2026-05-15 | Done | Frontend | 6
1.13 | Ph1 | Login & Register Pages | app/(auth)/login/page.tsx + register/page.tsx -- RHF+Zod, useAuth, pageVariants, Sonner toasts on success/error | Frontend Dev | 2026-05-15 | 2026-05-17 | Done | Frontend | 8
1.14 | Ph1 | Route Guard | middleware.ts: redirect unauthenticated /dashboard/* to /login. (dashboard)/layout.tsx placeholder, redirect to /overview | Frontend Dev | 2026-05-17 | 2026-05-17 | Done | Frontend | 2
2.1 | Ph2 | Connector Model + Service | models/connector.py (encrypted tokens, status, sync_frequency), services/connector_service.py CRUD + save_tokens(), indexes | Backend Dev | 2026-05-18 | 2026-05-19 | Not Started | Backend | 6
2.2 | Ph2 | Connector CRUD Endpoints | routers/connectors.py: GET / POST / GET :id / PUT :id / DELETE :id -- all behind get_current_user dep | Backend Dev | 2026-05-19 | 2026-05-20 | Not Started | Backend | 5
2.3 | Ph2 | OAuth Shared Helpers | utils/oauth.py: PKCE code verifier/challenge, state nonce store (Redis), token-exchange wrapper for all platforms | Backend Dev | 2026-05-20 | 2026-05-20 | Not Started | Backend | 4
2.4 | Ph2 | Google Ads OAuth | platforms/google_ads.py: get_auth_url, exchange_code, refresh_access_token. GET /connectors/google_ads/auth + /callback | Backend Dev | 2026-05-20 | 2026-05-21 | Not Started | Backend | 6
2.5 | Ph2 | GA4 OAuth | platforms/ga4.py (reuse Google Cloud client, enable GA4 Data API). GET /connectors/ga4/auth + /callback | Backend Dev | 2026-05-21 | 2026-05-21 | Not Started | Backend | 4
2.6 | Ph2 | Facebook Ads OAuth | platforms/facebook_ads.py (Meta Marketing API). GET /connectors/facebook_ads/auth + /callback | Backend Dev | 2026-05-21 | 2026-05-22 | Not Started | Backend | 5
2.7 | Ph2 | Frontend Connector Types+Hooks | types/connector.ts (IConnector, Platform enum), hooks/useConnectors.ts (list/get/create/update/delete + cache invalidation) | Frontend Dev | 2026-05-18 | 2026-05-19 | Not Started | Frontend | 4
2.8 | Ph2 | Shared UI -- Second Batch | SyncStatusBadge, ConnectorCard (logo+status+timestamp), ResponsiveModal (Dialog to Sheet on mobile), ConfirmDialog | Frontend Dev | 2026-05-19 | 2026-05-21 | Not Started | Frontend | 6
2.9 | Ph2 | Add Connector Modal | connectors/AddConnectorModal.tsx: platform picker, sync_frequency (RHF+Zod), OAuth redirect trigger, Sonner feedback | Frontend Dev | 2026-05-21 | 2026-05-22 | Not Started | Frontend | 6
2.10 | Ph2 | Connectors Page Initial | connectors/page.tsx + ConnectorGrid.tsx: listContainerVariants stagger, empty state, loading skeleton | Frontend Dev | 2026-05-22 | 2026-05-23 | Not Started | Frontend | 6
2.11 | Ph2 | OAuth Callback Handler | connectors/OAuthCallback.tsx: reads ?connected=platform, toast.success, invalidates RQ connectors cache | Frontend Dev | 2026-05-23 | 2026-05-24 | Not Started | Frontend | 3
3.1 | Ph3 | Marketing Data Model | models/marketing_data.py (unified schema: metrics+dimensions), unique compound index (user_id, platform, date, campaign_id) | Backend Dev | 2026-05-25 | 2026-05-25 | Not Started | Backend | 3
3.2 | Ph3 | Celery + Redis Bootstrap | tasks/celery_app.py: Celery+Beat hourly schedule, Compose celery-worker+celery-beat, get_sync_db() sync wrapper | Backend Dev | 2026-05-25 | 2026-05-26 | Not Started | Backend | 5
3.3 | Ph3 | Sync Service Core | services/sync_service.py upsert logic, tasks/sync_tasks.py: sync_connector (status transitions, retry x3) + run_scheduled_syncs | Backend Dev | 2026-05-26 | 2026-05-28 | Not Started | Backend | 8
3.4 | Ph3 | Google Ads fetch_data | Add fetch_data(connector) to google_ads.py -- map API response to unified marketing_data schema | Backend Dev | 2026-05-28 | 2026-05-29 | Not Started | Backend | 6
3.5 | Ph3 | GA4 fetch_data | Add fetch_data(connector) to ga4.py -- session/user metrics mapped to unified schema | Backend Dev | 2026-05-29 | 2026-05-29 | Not Started | Backend | 5
3.6 | Ph3 | Facebook Ads fetch_data | Add fetch_data(connector) to facebook_ads.py -- campaign insights to unified schema, handle pagination | Backend Dev | 2026-05-29 | 2026-05-30 | Not Started | Backend | 5
3.7 | Ph3 | Sync Trigger + Status Endpoints | POST /sync/trigger/:id (enqueue Celery), GET /sync/status (all connectors), GET /sync/history/:id (last 20 runs) | Backend Dev | 2026-05-26 | 2026-05-27 | Not Started | Backend | 5
3.8 | Ph3 | LinkedIn Ads OAuth + Sync | platforms/linkedin.py: get_auth_url, exchange_code, fetch_data. GET /connectors/linkedin_ads/auth + /callback | Backend Dev | 2026-05-30 | 2026-05-31 | Not Started | Backend | 7
3.9 | Ph3 | TikTok Ads OAuth + Sync | platforms/tiktok.py: TikTok for Business API, OAuth + fetch_data upsert. GET /connectors/tiktok_ads/auth + /callback | Backend Dev | 2026-05-30 | 2026-05-31 | Not Started | Backend | 7
3.10 | Ph3 | Frontend Sync Hooks + UI | hooks/useSync.ts (useSyncStatus poll 30s, useTriggerSync, useSyncHistory), ConnectorCard trigger btn + live badge | Frontend Dev | 2026-05-28 | 2026-05-31 | Not Started | Frontend | 5
4.1 | Ph4 | GET /reports/overview | $match + $group + $sum (spend/clicks/impressions/conv/revenue) by platform, period-over-period delta in response | Backend Dev | 2026-05-25 | 2026-05-27 | Not Started | Backend | 6
4.2 | Ph4 | GET /reports/campaigns | Paginated list (page+limit), filter by platform+date range, sort by spend desc | Backend Dev | 2026-05-27 | 2026-05-29 | Not Started | Backend | 5
4.3 | Ph4 | GET /reports/trend | Daily/weekly time-series: $group by date, metric selector (spend/clicks/roas etc.) | Backend Dev | 2026-05-29 | 2026-05-31 | Not Started | Backend | 5
4.4 | Ph4 | POST /reports/custom | Body: {metrics, dimensions, filters, chart_type} -> dynamic aggregation pipeline -> execute -> return result | Backend Dev | 2026-06-01 | 2026-06-03 | Not Started | Backend | 6
4.5 | Ph4 | Saved Reports CRUD | models/report.py, GET/POST/GET:id/DELETE /reports/saved -- persist custom report params + chart_type for replay | Backend Dev | 2026-06-03 | 2026-06-05 | Not Started | Backend | 6
4.6 | Ph4 | CSV Export | GET /reports/export?format=csv -- StreamingResponse CSV from same aggregation as /custom | Backend Dev | 2026-06-05 | 2026-06-05 | Not Started | Backend | 3
4.7 | Ph4 | Frontend Types + Hooks | types/report.ts + types/campaign.ts, hooks/useReports.ts (overview/trend/custom/saved), hooks/useCampaigns.ts | Frontend Dev | 2026-06-02 | 2026-06-04 | Not Started | Frontend | 5
4.8 | Ph4 | Shared UI -- Third Batch | DataTable (sortable, mobile-collapse), Pagination, SearchInput (debounced), DateRangePicker, KpiCard -- log in componentsHistory.md | Frontend Dev | 2026-06-01 | 2026-06-04 | Not Started | Frontend | 8
4.9 | Ph4 | Chart Components | SpendTrendChart (line), PlatformDonut (pie), CampaignBarChart (bar), RoasGauge (radial) -- fadeVariants on mount | Frontend Dev | 2026-06-04 | 2026-06-07 | Not Started | Frontend | 8
5.1 | Ph5 | App Layout Shell | Sidebar.tsx (collapsible, active border-l-2, whileHover x:2), Header.tsx (ThemeToggle+avatar), (dashboard)/layout.tsx, uiStore.ts | Frontend Dev | 2026-06-01 | 2026-06-03 | Not Started | Frontend | 8
5.2 | Ph5 | Overview Page | OverviewGrid.tsx (6 KpiCards stagger), overview/page.tsx: KPI grid + SpendTrendChart + PlatformDonut + campaigns DataTable | Frontend Dev | 2026-06-03 | 2026-06-07 | Not Started | Frontend | 8
5.3 | Ph5 | Campaigns Page | campaigns/page.tsx: DataTable + Pagination + DateRangePicker + platform filter + SearchInput | Frontend Dev | 2026-06-07 | 2026-06-09 | Not Started | Frontend | 5
5.4 | Ph5 | Report Builder | MetricSelector.tsx (multi-select), FilterPanel.tsx (platform+date+dims), ReportBuilder.tsx (chart toggle + save) -- RHF+Zod | Frontend Dev | 2026-06-08 | 2026-06-12 | Not Started | Frontend | 10
5.5 | Ph5 | Reports Pages | reports/page.tsx (saved list + ReportBuilder), reports/[id]/page.tsx (saved detail), CSV export download button | Frontend Dev | 2026-06-12 | 2026-06-14 | Not Started | Frontend | 6
6.1 | Ph6 | AI Pipeline Generator | ai_service.py: generate_pipeline(question, schema, user_id) -> Claude (claude-sonnet-4-6) -> validated aggregation array | AI Dev | 2026-06-08 | 2026-06-11 | Not Started | Backend | 8
6.2 | Ph6 | AI Executor + Explainer | Execute pipeline on marketing_data, second Claude call for plain-English explanation, persist {question, pipeline, result, explanation} | AI Dev | 2026-06-11 | 2026-06-13 | Not Started | Backend | 6
6.3 | Ph6 | AI Endpoints | POST /ai/query (validate + call ai_service), GET /ai/history (paginated past queries per user) | AI Dev | 2026-06-13 | 2026-06-14 | Not Started | Backend | 3
6.4 | Ph6 | Frontend AI Hook | hooks/useAi.ts: useAiQuery (mutation), useAiHistory (query with [ai, history] RQ key) | Frontend Dev | 2026-06-15 | 2026-06-15 | Not Started | Frontend | 3
6.5 | Ph6 | AI Panel + Result Card | AiQueryPanel.tsx (NL input + history sidebar), AiResultCard.tsx (explanation + collapsible pipeline + Recharts auto-chart) | Frontend Dev | 2026-06-15 | 2026-06-20 | Not Started | Frontend | 10
6.6 | Ph6 | AI Page | app/(dashboard)/ai/page.tsx -- AiQueryPanel + AiResultCard, pageVariants entry animation | Frontend Dev | 2026-06-20 | 2026-06-21 | Not Started | Frontend | 3
7.1 | Ph7 | Profile + Password Endpoints | PUT /auth/me (update name/email), PUT /auth/password (verify current, hash new, revoke active refresh tokens) | Backend Dev | 2026-06-15 | 2026-06-16 | Not Started | Backend | 5
7.2 | Ph7 | Notifications Backend | models/notification.py, emit on sync success/error in sync_tasks.py, GET /notifications + PATCH :id/read + POST /read-all | Backend Dev | 2026-06-16 | 2026-06-19 | Not Started | Backend | 8
7.3 | Ph7 | Settings Page | settings/page.tsx: Profile + Password + Plan badge + API key (read-only) -- shadcn Tabs, RHF+Zod, Sonner toasts | Full Stack Dev | 2026-06-17 | 2026-06-20 | Not Started | Full Stack | 7
7.4 | Ph7 | Notification Bell | NotificationBell.tsx in Header: unread badge, dropdown list, poll /notifications 60s, Sonner on new sync events | Frontend Dev | 2026-06-20 | 2026-06-21 | Not Started | Frontend | 5
8.1 | Ph8 | Docker Compose Full Stack | All 6 services (backend, celery-worker, celery-beat, mongo, redis, frontend) with healthchecks + volume mounts | DevOps | 2026-06-22 | 2026-06-23 | Not Started | Infra | 8
8.2 | Ph8 | Backend Dockerfile | Multi-stage build, non-root user, uvicorn+gunicorn workers, .dockerignore | DevOps | 2026-06-22 | 2026-06-22 | Not Started | Infra | 4
8.3 | Ph8 | Frontend Dockerfile | Next.js standalone output build, next start runtime, .dockerignore (exclude node_modules, .next/cache) | DevOps | 2026-06-22 | 2026-06-22 | Not Started | Infra | 3
8.4 | Ph8 | Railway Deploy (Backend) | Two services: web (FastAPI) + worker (Celery+Beat), env vars from Railway secrets, health check on /health | DevOps | 2026-06-23 | 2026-06-25 | Not Started | Infra | 8
8.5 | Ph8 | Vercel Deploy (Frontend) | Connect repo to Vercel, set NEXT_PUBLIC_API_URL to Railway URL, preview + production environments | DevOps | 2026-06-23 | 2026-06-24 | Not Started | Infra | 4
8.6 | Ph8 | Managed Data Plane | MongoDB Atlas M0 cluster + IP allowlist, Upstash Redis instance + URL wired into Railway env vars | DevOps | 2026-06-24 | 2026-06-25 | Not Started | Infra | 4
8.7 | Ph8 | Observability | Sentry SDK backend (sentry_sdk[fastapi]) + frontend (@sentry/nextjs), UptimeRobot monitor on /health endpoint | DevOps | 2026-06-25 | 2026-06-27 | Not Started | Infra | 6
8.8 | Ph8 | Final Docs | README.md run instructions, PROJECT_STATUS.md all 67 features done, verify all .md history files match shipped code | Full Stack Dev | 2026-06-27 | 2026-06-28 | Not Started | Full Stack | 4
TOTALS -- Estimated Hours / Actual Hours

## Suggestions & Approvals
TEAM SUGGESTIONS & HIGHER-UP APPROVALS
Any team member can submit a suggestion below. Higher-ups review and mark Approved / Rejected with comments.
ID | Phase Ref | Submitted By | Suggestion / Feature Request | Impact Level | Submitted Date | Decision | Approved By | Decision Date | Comments / Reason
S-001
S-002
S-003
S-004
S-005
S-006
S-007
S-008
S-009
S-010
S-011
S-012
S-013
S-014
S-015
S-016
S-017
S-018
S-019
S-020